| PROGRESS REPORT ON THE ONGOING PROJECTS FUNDED BY THE ROAD MAINTENANCE FUND/ BUDGET YEAR 2011-2012 - RTDA/MININFRA |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| SNo | CONTRACT NUMBER | PROJECT | REVISED CONTRACT AMOUNT | PAYMENT BETWEEN JULY 2011 - FEBRUARY 2012 |  | CUMULATIVE PAYMENT | BALANCE |  | PHYSICAL IMPLEMENTATION |  |  |  |  |  |  |  |
| 1 | 34/FER/2008 | Detailed study and supervision of periodic maintenance works of Cyakabiri - Nyabikenke - Ndusu (Lot I & Lot II) | 167,985,500 | 4,805,000 |  | 162,825,500 | 5,160,000 |  | Lot I has been completed and provisionally handed over, but Lot II is not yet handed over. The Contractor has requested for handover. |  |  |  |  |  |  |  |
| 2 | 36/FER/2008 | Detailed study and supervision of periodic maintenance works of Kazabe - Rutsiro - Gashubi earth road | 120,910,000 | 28,008,000 |  | 104,082,000 | 16,828,000 |  | The Contractor has not yet completed the works and the Supervisor has to remain on site. |  |  |  |  |  |  |  |
| 3 | 53/FER/2008 | Recurrent maintenance of KIGALI - GATUNA road (78 KM) | 402,891,500 | 88,128,300 |  | 382,849,300 | 20,042,200 |  | Completed and handed over (Final handover). (100%). |  |  |  |  |  |  |  |
| 4 | 69/FER/2008 | Etude et surveillance de l'Entretien periodique de la route Ngororero-Vunga-Nyakinama et la bretelle Gitega-Gatumba | 175,964,550 | 50,940,600 |  | 88,847,710 | 87,116,840 |  | Ongoing. The Contractor for Lot I has been given completion period extension and Lot II has not yet started. |  |  |  |  |  |  |  |
| 5 | RMF/2009-2010/05 BIS | Periodic maintenance of BRALIRWA - Nyamwenda - Nkora earth road | 1,704,280,500 | 98,262,261 |  | 1,704,263,833 | 16,667 |  | Completed and final handover (100%) |  |  |  |  |  |  |  |
| SNo | CONTRACT NUMBER | PROJECT | REVISED CONTRACT AMOUNT | PAYMENT BETWEEN JULY 2011 - FEBRUARY 2012 |  | CUMULATIVE PAYMENT | BALANCE |  | PHYSICAL IMPLEMENTATION |  |  |  |  |  |  |  |
| 6 | RMF/2009 - 2010/14 & RMF/2010-2011/38 | Supervision of periodic maintenance of Butare - Kibeho - Muse earth road (second contract) | 88.181,400 | 0 |  | 78,871,200 | 9,310,200 |  | Completed (100%) |  |  |  |  |  |  |  |
| 7 | RMF/2009 - 2010/23 | Periodic maintenance of Pindura - Bweyeye earth road | 1,993,025,950 | 0 |  | 388,374,246 | 1,604,651,704 |  | The Contract is under termination as the delay penalties period has ended while the works progress was estimated near 40%. |  |  |  |  |  |  |  |
| 8 | RMF/2009 - 2010/29 | Supervision of periodic maintenance works of Pindura - Bweyeye road | 70,228,800 | 0 |  | 60,387,595 | 9,841,205 |  | As the Contractor is in contract termination process, the Supervisor is no longer on site. |  |  |  |  |  |  |  |
| 9 | RMF/2009 - 2010/32 | Emergency works for rehabilitation of Karuruma - Jali earth road | 490,606,535 | 0 |  | 455,267,835 | 35,338,700 |  | Completed and provisionally handed over (100%) |  |  |  |  |  |  |  |
| 10 | RMF/2009 - 2010/33 | Periodic maintenance of Mudasomwa - Gisovu earth road (53 km) | 3,662,012,295 | 676,257,885 |  | 3,460,526,858 | 201,485,437 |  | Completed at 100%, but the handover process is not yet finished. |  |  |  |  |  |  |  |
| 11 | RMF/2009 - 2010/35 | Supervision of periodic maintenance works of Mudasomwa - Gisovu road | 100,180,025 | 12,555,790 |  | 95,218,623 | 4,961,402 |  | Completed (100%) |  |  |  |  |  |  |  |
| SNo | CONTRACT NUMBER | PROJECT | REVISED CONTRACT AMOUNT | PAYMENT BETWEEN JULY 2011 - FEBRUARY 2012 |  | CUMULATIVE PAYMENT | BALANCE |  | PHYSICAL IMPLEMENTATION |  |  |  |  |  |  |  |
| 12 | RMF/2009 - 2010/53 | Periodic maintenance of Pont Masizi - Ndusu earth road (Lot II Cyakabiri - Nyabikenke - Ndusu) | 3,020,371,003 | 854,137,959 |  | 1,576,019,187 | 1,444,351,816 |  | The Contractor has been working under delay penalties since 21st September 2011. He has now requested for provisional handover. The works progress is now estimated at 95%. |  |  |  |  |  |  |  |
| 13 | RMF/2009 - 2010/55 | Periodic maintenance of Byimana - Buhanda - Kaduha earth road (49km) | 2,603,957,932 | 976,579,014 |  | 2,322,645,041 | 281,312,891 |  | Completed at 100% and provisionally handed over. |  |  |  |  |  |  |  |
| 14 | RMF/2009 - 2010/56 | Periodic maintenance of Cyakabiri - Pont Masizi earth road (Lot I Cyakabiri - Nyabikenke - Ndusu) | 3,118,997,587 | 1,189,773,379 |  | 2,513,954,683 | 605,042,904 |  | Completed at 100% and provisionally handed over. |  |  |  |  |  |  |  |
| 15 | RMF/2009 - 2010/65 | Supervision of maintenance works on roads connected to Gitarama - Ngororero - Mukamira | 48,462,600 | 1,640,200 |  | 48,462,600 | 0 |  | Completed (100%) |  |  |  |  |  |  |  |
| 16 | RMF/2010 - 2011/01 | Supervision of periodic maintenance of Byimana - Buhanda - Kaduha road | 75,284,000 | 15,351,800 |  | 69,631,800 | 5,652,200 |  | Completed (100%) |  |  |  |  |  |  |  |
| 17 | RMF/2010 - 2011/04 | Routine maintenance (cantonnage) of Cyanika - Ruhengeri - Nyakinama road | 13,716,000 | 4,073,500 |  | 13,377,499 | 338,501 |  | Completed (100%) |  |  |  |  |  |  |  |
| SNo | CONTRACT NUMBER | PROJECT | REVISED CONTRACT AMOUNT | PAYMENT BETWEEN JULY 2011 - FEBRUARY 2012 |  | CUMULATIVE PAYMENT | BALANCE |  | PHYSICAL IMPLEMENTATION |  |  |  |  |  |  |  |
| 18 | RMF/2010 - 2011/06 | Construction of cobbled stone paved roads in Taba, Huye District, Lot II & III | 1,463,023,796 | 231,120,116 |  | 1,098,501,883 | 364,521,913 |  | Completed (100%) and provisionally handed over |  |  |  |  |  |  |  |
| 19 | RMF/2010 - 2011/08 | Periodic maintenance of Kazabe - Rutsiro - Gashubi earth road | 3,392,802,054 | 290,578,523 |  | 580,942,863 | 2,811,859,191 |  | The works are still ongoing and the progress is estimated at 50% as the extension period has ended on 15th February 2012. |  |  |  |  |  |  |  |
| 20 | RMF/2010 - 2011/09 | Detailed study and supervision of retaining wall construction and watercourse development at Gisiza | 14,997,800 | 4,141,800 |  | 4,141,800 | 10,856,000 |  | The study has been completed and the supervision also has been completed (100%). |  |  |  |  |  |  |  |
| 21 | RMF/2010 - 2011/13 | Maintenance for three years of Gitarama - Kibuye asphalt road (74 km) (First year) | 1,720,014,551 | 1,660,396,012 |  | 1,660,396,012 | 59,618,539 |  | Completed (100%) and provisionally handed over. |  |  |  |  |  |  |  |
| 22 | RMF/2010 - 2011/15 | Maintenance for three years of Kayonza - Kagitumba asphalt road (First year) | 2,773,049,206 | 0 |  | 0 | 2,773,049,206 |  | The first year works were provisionally handed over. The progress is estimated at 100%. |  |  |  |  |  |  |  |
| 23 | RMF/2010 - 2011/16 | Maintenance for three years of Kayonza - Rusumo asphalt road (First year) | 1,999,230,906 | 1,188,991,023 |  | 1,325,351,528 | 673,879,378 |  | The first year works were provisionally handed over. The progress is estimated at 100%. |  |  |  |  |  |  |  |
| SNo | CONTRACT NUMBER | PROJECT | REVISED CONTRACT AMOUNT | PAYMENT BETWEEN JULY 2011 - FEBRUARY 2012 |  | CUMULATIVE PAYMENT | BALANCE |  | PHYSICAL IMPLEMENTATION |  |  |  |  |  |  |  |
| 24 | RMF/2010 - 2011/18 | Protection works of upstream and the bridge on PK 6+400 of Musanze - Rubavu road | 33,429,000 | 10,724,106 |  | 33,429,000 | 0 |  | Completed and final handed over (100%) |  |  |  |  |  |  |  |
| 25 | RMF/2010 - 2011/19 / RMF/2011-2012/09 | Supervision of stone paved roads construction in Taba, Huye District | 52,756,250 | 22,362,500 |  | 50,923,750 | 1,832,500 |  | The Lots II & III have been completed but the Lot I is not yet handed over. |  |  |  |  |  |  |  |
| 26 | RMF/2010 - 2011/21 | Supervision of maintenance works on roads connected to Gitarama - Ngororero - Mukamira (Ngororero - Kavumu and Rubaya - Kabaya), second contract | 21,971,600 | 3,917,600 |  | 21,971,600 | 0 |  | Completed (100%) |  |  |  |  |  |  |  |
| 27 | RMF/2010 - 2011/27 | Supervision of Karuruma Jali maintenance works | 37,482,700 | 0 |  | 35,417,700 | 2,065,000 |  | Completed (100%) |  |  |  |  |  |  |  |
| 28 | RMF/2010 - 2011/28 | Consulting services for the preparation of environmental impact assessment on Brasserie - Nyamwenda - Nkora road | 12,083,200 | 2,416,640 |  | 12,083,200 | 0 |  | Completed (100%) |  |  |  |  |  |  |  |
| 29 | RMF/2010 - 2011/31 | Emergency works for Gashora 4 bridge rehabilitation | 166,079,100 | 89,880,600 |  | 165,406,500 | 672,600 |  | Completed (100%) and provisionally handed over |  |  |  |  |  |  |  |
| SNo | CONTRACT NUMBER | PROJECT | REVISED CONTRACT AMOUNT | PAYMENT BETWEEN JULY 2011 - FEBRUARY 2012 |  | CUMULATIVE PAYMENT | BALANCE |  | PHYSICAL IMPLEMENTATION |  |  |  |  |  |  |  |
| 30 | RMF/2010 - 2011/32 | Detailed study for rehabilitation of tea factories access roads (Mugashinge - Murambya) road) | 14,962,400 | 0 |  | 7,481,200 | 7,481,200 |  | The final version of the study has not yet been approved. |  |  |  |  |  |  |  |
| 31 | RMF/2010 - 2011/33 | Detailed study for rehabilitation of tea factories access roads (Rugabano - Gasenyi road) | 16,402,000 | 8,201,000 |  | 16,402,000 | 0 |  | Completed (100%) |  |  |  |  |  |  |  |
| 32 | RMF/2010 - 2011/34 | Detailed study for rehabilitation of tea factories access roads (Gisovu - Kivugiza road) | 28,000,000 | 0 |  | 14,000,000 | 14,000,000 |  | The final version of the study has not yet been approved. |  |  |  |  |  |  |  |
| 33 | RMF/2010 - 2011/35 | Agreement for power cables and water pipes displacement on Huye stone pavement construction site | 119,206,675 | 0 |  | 0 | 119,206,675 |  | EWSA has completed the works but no invoice has reached FER yet. |  |  |  |  |  |  |  |
| 34 | RMF/2010 - 2011/36 | Agreement for telephone cables displacement on Huye stone pavement construction site | 149,513,055 | 0 |  | 0 | 149,513,055 |  | The cables have been displaced but no invoice has reached FER yet. |  |  |  |  |  |  |  |
| 35 | RMF/2010 - 2011/37 | Agreement for technical assistance for the execution of Huye stone pavement works | 134,768,611 | 108,186,439 |  | 134,765,779 | 2,832 |  | As the works for Lot I have not yet been handed over, the technical assistance is still ongoing. |  |  |  |  |  |  |  |
| SNo | CONTRACT NUMBER | PROJECT | REVISED CONTRACT AMOUNT | PAYMENT BETWEEN JULY 2011 - FEBRUARY 2012 |  | CUMULATIVE PAYMENT | BALANCE |  | PHYSICAL IMPLEMENTATION |  |  |  |  |  |  |  |
| 36 | RMF/2010 - 2011/40 | Retaining wall construction and water stream protection at Gisiza (PK 27+600) on Rubengera - Rugerero road | 202,722,702 | 74,026,269 |  | 121,986,732 | 80,735,970 |  | The works have been completed (100%) and the handover process is ongoing. |  |  |  |  |  |  |  |
| 37 | RMF/2010-2011/42 | Emergency works for Karongi tea factory access road rehabilitation | 391,601,880 | 271,725,680 |  | 391,601,880 | 0 |  | Completed (100%) and final handover done |  |  |  |  |  |  |  |
| 38 | RMF/2010-2011/43 | Supervision of multiyear periodic maintenance of Gitarama - Kibuye, Kayonza - Rusumo and Kayonza - Kagitumba asphalt roads | 517,754,826 | 381,419,831 |  | 381,419,831 | 136,334,995 |  | The first year of supervision is completed and the second year is ongoing. |  |  |  |  |  |  |  |
| 39 | RMF/2010-2011/44 | Protection and maintenance of Brasserie - Nyamwenda - Nkora earth road | 398,984,000 | 24,283,750 |  | 398,984,000 | 0 |  | Completed and final handed over done. |  |  |  |  |  |  |  |
| 40 | RMF/2010-2011/46 | Rehabilitation of deteriorated sections on Kibuye - Cyangugu road | 126,030,200 | 25,251,550 |  | 126,030,200 | 0 |  | Completed and provisionally handed over |  |  |  |  |  |  |  |
| 41 | RMF/2010-2011/47 | Detailed study for rehabilitation of Nyabihu new hydropower plant access road: road Jomba - Shyira (18 km) | 18,054,000 | 9,027,000 |  | 18,054,000 | 0 |  | Completed (100%) |  |  |  |  |  |  |  |
| SNo | CONTRACT NUMBER | PROJECT | REVISED CONTRACT AMOUNT | PAYMENT BETWEEN JULY 2011 - FEBRUARY 2012 |  | CUMULATIVE PAYMENT | BALANCE |  | PHYSICAL IMPLEMENTATION |  |  |  |  |  |  |  |
| 42 | RMF/2010-2011/49 | Construction of cobbled stone paved roads in Taba, Huye District; Lot I | 1,504,411,111 | 1,090,766,090 |  | 1,090,766,090 | 413,645,021 |  | The works have been completed (98%), the Contractor has requested for provisional handover. |  |  |  |  |  |  |  |
| 43 | RMF/2010-2011/51 | Supervision of protection works on Brasserie - Nyamwenda - Nkora road | 26,585,400 | 3,599,000 |  | 26,196,000 | 389,400 |  | Completed (100%). |  |  |  |  |  |  |  |
| 44 | RMF/2010-2011/53 | Construction of KAVILI Bridge (Nyanza District) | 107,459,060 | 107,208,314 |  | 107,208,314 | 250,746 |  | Completed (100%) and provisionally handed over |  |  |  |  |  |  |  |
| 45 | RMF/2010-2011/55 | Emergency works for Cyaruhogo dyke construction, on Rwamagana - Zaza earth road | 354,929,000 | 262,809,870 |  | 262,809,870 | 92,119,130 |  | Works completed and provisional handover done. |  |  |  |  |  |  |  |
| 46 | RMF/2010-2011/62 | Routine maintenance (cantonnage) of Kigali - Gatuna road for two months | 5,936,000 | 5,936,000 |  | 5,936,000 | 0 |  | Completed (100%) |  |  |  |  |  |  |  |
| 47 | RMF/2010-2011/63 | Routine maintenance (cantonnage) of Kigali - Kayonza road for two months | 6,477,334 | 6,477,334 |  | 6,477,334 | 0 |  | Completed (100%) |  |  |  |  |  |  |  |
| 48 | RMF/2010-2011/64 | Routine maintenance (cantonnage) of Cyangugu - Bugarama - Ruhwa road for two months | 3,830,956 | 3,619,822 |  | 3,619,822 | 211,134 |  | Completed (100%) |  |  |  |  |  |  |  |
| SNo | CONTRACT NUMBER | PROJECT | REVISED CONTRACT AMOUNT | PAYMENT BETWEEN JULY 2011 - FEBRUARY 2012 |  | CUMULATIVE PAYMENT | BALANCE |  | PHYSICAL IMPLEMENTATION |  |  |  |  |  |  |  |
| 49 | RMF/2010-2011/65 | Emergency works for maintenance of Gakoma - Rukarara hydropower plant access road | 429,480,258 | 429,071,588 |  | 429,071,588 | 408,670 |  | Completed (100%) and provisionally handed over |  |  |  |  |  |  |  |
| 50 | RMF/2010-2011/66 | Rehabilitation and periodic maintenance of Nyakinama - Satinsyi earth road | 1,740,583,720 | 0 |  | 0 | 1,740,583,720 |  | The contract has been signed but the works have not yet started due to one of the bidders’ claim. |  |  |  |  |  |  |  |
| 51 | RMF/2011-2012/02 | Execution of urgent maintenance works of Gitarama-Huye-Akanyaru and Huye -Kitabi | 458,566,809 | 0 |  | 0 | 458,566,809 |  | The works are ongoing even though the contract period has ended. |  |  |  |  |  |  |  |
| 52 | RMF/2011-2012/03 | Emergency works of bridge rehabilitation on Koko River on Rubengera Pfunda road | 25,006,000 | 0 |  | 0 | 25,006,000 |  | Ongoing |  |  |  |  |  |  |  |
| 53 | RMF/2011-2012/04 | Emergency works of drainage for the roads sections: Kicukiro-Nyamata, Kigali-Gatuna , Kigali Kayonza | 130,723,498 | 112,840,533 |  | 112,840,533 | 17,882,965 |  | Completed (100%) and provisionally handed over. |  |  |  |  |  |  |  |
| 54 | RMF/2011-2012/07 | Consultant service for control and supervision of the emergency works of maintenance of Gakoma Rukarara access road to Rukarara hydropower plant (8.6 km) | 23,458,400 | 12,342,800 |  | 12,342,800 | 11,115,600 |  | Completed (100%) and the final report provided. |  |  |  |  |  |  |  |
| SNo | CONTRACT NUMBER | PROJECT | REVISED CONTRACT AMOUNT | PAYMENT BETWEEN JULY 2011 - FEBRUARY 2012 |  | CUMULATIVE PAYMENT | BALANCE |  | PHYSICAL IMPLEMENTATION |  |  |  |  |  |  |  |
| 55 | RMF/2011-2012/10 | Supervision of periodic maintenance works of Pindura - Bweyeye road / New contract | 45,231,760 | 0 |  | 0 | 45,231,760 |  | The Contractor contract is in termination process; no supervision done on site. |  |  |  |  |  |  |  |
| 56 | RMF/2011-2012/17 | Emergency works for the construction of Giciye bridge on hydropower plant site in Nyabihu District | 236,736,250 | 0 |  | 0 | 236,736,250 |  | Ongoing |  |  |  |  |  |  |  |
| 57 | RMF/2011-2012/19 | Routine maintenance of Kigali - Gatuna asphalt road (78 km) | 37,149,000 | 0 |  | 0 | 37,149,000 |  | Ongoing (Works progress estimated at 25%) |  |  |  |  |  |  |  |
| 58 | RMF/2011-2012/20 | Routine maintenance of Cyangugu - Bugarama - Ruhwa asphalt road (53km) | 22,017,310 | 0 |  | 0 | 22,017,310 |  | The winning bidder has provided a forged performance guarantee, and the contract has been cancelled. |  |  |  |  |  |  |  |
| 59 | RMF/2011-2012/21 | Routine maintenance of Ruhengeri - Gisenyi - Bralirwa asphalt road (70 km) | 36,638,430 | 0 |  | 0 | 36,638,430 |  | The winning bidder has provided a forged performance guarantee, and the contract has been cancelled. |  |  |  |  |  |  |  |
| 60 | RMF/2011-2012/22 | Routine maintenance of Kigali - Gitarama asphalt road (47 km) | 21,441,560 | 0 |  | 0 | 21,441,560 |  | Ongoing (Works progress estimated at 25%) |  |  |  |  |  |  |  |
| SNo | CONTRACT NUMBER | PROJECT | REVISED CONTRACT AMOUNT | PAYMENT BETWEEN JULY 2011 - FEBRUARY 2012 |  | CUMULATIVE PAYMENT | BALANCE |  | PHYSICAL IMPLEMENTATION |  |  |  |  |  |  |  |
| 61 | RMF/2011-2012/23 | Routine maintenance of Kigali - Kayonza asphalt road (65 km) | 26,582,600 | 0 |  | 0 | 26,582,600 |  | Ongoing (Works progress estimated at 25%) |  |  |  |  |  |  |  |
| 62 | RMF/2011-2012/24 | Routine maintenance of Ruhengeri - Nyakinama - Cyanika asphalt road (34 km) | 14,668,000 | 0 |  | 0 | 14,668,000 |  | Ongoing (Works progress estimated at 25%) |  |  |  |  |  |  |  |
| 63 | RMF/2011-2012/25 | Routine maintenance of Kicukiro - Nemba asphalt road (61 km) | 26,008,000 | 0 |  | 0 | 26,008,000 |  | Ongoing (Works progress estimated at 20%) |  |  |  |  |  |  |  |
| 64 | RMF/2011-2012/29 | Routine maintenance of Gitarama - Ngororero asphalt road (46.6 km) | 21,425,000 | 0 |  | 0 | 21,425,000 |  | Ongoing (Works progress estimated at 25%) |  |  |  |  |  |  |  |
| 65 | RMF/2011-2012/27 | Maintenance for three years of Gitarama - Kibuye asphalt road (74 km) (First year) | 1,710,325,571 | 0 |  | 0 | 1,710,325,571 |  | The second year has started in January 2012. |  |  |  |  |  |  |  |
| 66 | RMF/2011-2012/31 | Urgent works or removal of landslide at Base Burera and Burera -Butaro road | 30,000,000 | 0 |  | 0 | 30,000,000 |  | Works completed and provisionally handed over. |  |  |  |  |  |  |  |
| 67 | RMF/2011-2012/32 | Urgent works for the diversion of Nyabarongo riverbanks at PK 33+500 Muhanga-Ngororero road | 166,770,714 | 0 |  | 0 | 166,770,714 |  | The contract has been signed recently but the works were supposed to be completed by now. |  |  |  |  |  |  |  |
|  | TOTAL |  | 38,861,981,230 | 10,441,835,478 |  | 22,182,165,319 | 16,679,815,911 |  |  |  |  |  |  |  |  |  |

PROGRESS REPORT ON THE ONGOING PROJECTS FUNDED BY THE ROAD MAINTENANCE FUND/ BUDGET YEAR 2011-2012 - CITY OF KIGALI

SNo; CONTRACT NUMBER; CONTRACT NAME; REVISED CONTRACT AMOUNT; PAYMENT BETWEEN JULY 2011 - FEBRUARY 2012; CUMULATIVE PAYMENT; BALANCE; PHYSICAL IMPLEMENTATION. 1; RMF/2009 - 2010/02; Construction of Nyarutarama cobbled stone roads ( 9km); 1,209,476,501; 0; 915,667,039; 293,809,462; Completed and provisionally handed over. 2; RMF/2009 - 2010/08; Construction of 1,63 km of asphalt concrete roads in Kigali City; 551,228,026; 0; 510,519,615; 40,708,411; Completed. 3; RMF/2009 - 2010/09; Monitoring and supervision of Kigali City road upgrading works (36 km); 563,361,500; 79,933,200; 508,087,940; 55,273,560; Ongoing. 4; RMF/2009 - 2010/50; Supervision of construction of 5,92 km of asphalt concrete roads in Kigali City; 29,942,500; 7,375,000; 28,565,500; 1,377,000; Ongoing. 5; RMF/2009 - 2010/51; Construction of 5,92 km of asphalt concrete roads in Kigali City; 1,843,102,442; 220,211,398; 1,645,614,889; 197,487,553; Ongoing. 6; RMF/2010 - 2011/10; Repair works and maintenance of asphalt roads ad stone paved roads in Kigali City; 582,486,008; 96,569,247; 574,476,410; 8,009,598; Completed. 7; RMF/2010 - 2011/22; Supervision of construction works of 34,625 km asphalt concrete roads in Kigali City; 236,000,000; 101,598,000; 188,682,000; 47,318,000; Ongoing. 8; RMF/2010 - 2011/23; Construction of asphalt concrete roads in Kigali City (34,625 km); 13,748,266,005; 1,376,788,303; 2,587,250,705; 11,161,015,300; Ongoing. SNo; CONTRACT NUMBER; CONTRACT NAME; REVISED CONTRACT AMOUNT; PAYMENT BETWEEN JULY 2011 - FEBRUARY 2012; CUMULATIVE PAYMENT; BALANCE; PHYSICAL IMPLEMENTATION. 9; RMF/2010 - 2011/24; Detailed study of earth roads paving in Kicukiro District (Lot 3:31,2 km); 42,726,000; 21,363,000; 42,726,000; 0; Completed. 10; RMF/2010 - 2011/25; Detailed study of earth roads paving in Gasabo District (Lot 4:16,2 km); 23,718,000; 11,858,100; 23,718,000; 0; Completed. 11; RMF/2010 - 2011/26; Detailed study of earth roads paving in Nyarugenge District (Lot 2:20,2 km); 30,975,000; 15,487,500; 30,975,000; 0; Completed. 12; RMF/2010 - 2011/29; Detailed study of Rwandex - Sonatube - Prince House road rehabilitation (Lot I); 35,028,890; 17,514,445; 35,028,890; 0; Completed. 13; RMF/2010 - 2011/48; Supervision of cobbled stone pavement roads at NYARUTARAMA, second contract; 49,073,250; 0; 44,165,925; 4,907,325; Ongoing. 14; RMF/2010-2011/59; Supervision of construction of 5,92 km of asphalt concrete roads in Kigali City / Second contract; 20,915,500; 18,054,000; 18,054,000; 2,861,500; Ongoing. 15; RMF/2011-2012/30; Construction works of the asphalt concfrete road " cercle sportif - Nyamirambo"; 1,095,889,061; 0; 0; 1,095,889,061. TOTAL; 20,062,188,683; 1,966,752,193; 7,153,531,913; 12,908,656,770.

SUMMARY

During this budget year, from July 2011 up to now, FER has disbursed Ten billion four hundred and forty one million eight hundred thirty five thousand four hundred and seventy eight Rwandan Francs (10,441,835,478 RWF) on RTDA/MININFRA projects and One billion nine hundred forty five million seven hundred ninety nine thousand two hundred and forty eight Rwandan Francs (1,945,799,248 RWF) on City of KIGALI projects.